PROJECT CHARTER

Industry/FDA/Academia

Safety Graphics Working Group

Version 1.3 ● June 2, 2010, 2010

| VERSION: 1.3 | REVISION DATE: 06/02/10 |
| --- | --- |

Contents

Section 1	Overview	1

1.1	Problem Statement	1

1.2	Description	1

1.3	Goal	1

1.4	Project Scope	2

Section 2 	Milestones	3

2.1	High Level Project Plan	3

2.4	Major Project Deliverables	4

Section 3 	Project Organization	5

3.1	Core Membership 	5

3.2	Roles and Responsibilities	6

3.3	Project Facilities and Resources	7

Section 4 	Points of Contact	8

Section 5	Glossary	9

Section 6 	Revision History	10

# Section 1	Overview

## Problem Statement

Most presentations on safety data convey information in tabular form.  In general, tables are difficult to understand, especially when the data is complex. Graphics are more effective in conveying insight into complex safety data. The volume and complexity of current presentations of safety information complicate the review process and may cause important relationships to be missed over the life-cycle of the product. Rapid integration and dissemination of new information is often needed. The appropriate use of graphics can more effectively and efficiently communicate critical safety information to a variety of stakeholders.  Encouragement of consistent or standardized presentation of visual information is needed. There is a need to promote best practices in the use of graphical visualization of clinical safety information.

## Description

This is a joint working group among FDA, Industry, and Academia.

## Goal

The goal is to develop a palette of graphics for visualizations of clinical trial safety data.

  - Objectives

Upon completion of this project the group will:

  - Identify areas particularly applicable or useful to regulatory review in which graphics can enhance understanding of safety information.

  - Develop a palette of statistical graphics for reporting on clinical trials safety data.

  - Recommend graphics for clinical data based on good scientific principles and best practices.

  - Create a publicly-available repository of sample graphics (ensuring appropriate credits are given for contributions), including data sets and code.

  - Educate and engage stakeholders through outreach activities.

  - Consider publishing with authorship/acknowledgments as is consistent with contributions and policy of the affiliated institution.

## 1.4	Project Scope

Project Includes

Graphics to convey pre-approval clinical safety information, typically submitted in support of an integrated summary of safety (ISS).

Static graphics represented in; color, black and white, and grayscale.

Graphs for both descriptive and inferential purposes.

Static graphics should be printable.

Develop tools that will aide in the production of new drugs.

Project Excludes

Spontaneous reporting or epidemiological case control studies

Dynamic Graphics

# Section 2 	Milestones

## 2.1	High Level Project Plan

| High Level Project Plan | Planned Completion Date |
| --- | --- |
| Identify areas particularly applicable or useful to regulatory review in which graphics can enhance understanding of safety information. List major safety questions. What is the critical information needed to answer these questions? |  |
| Develop a palette of statistical graphics for specialized reporting of clinical trials data. Develop an inventory Recommend graphics for clinical data based on good graphical principles developed by individuals such as Willam Cleveland and Edward Tufte. Draw up what would be effective to address (a). |  |
| Create a publicly-available repository of sample graphics (ensuring appropriate credits are given for contributions), including data sets and sample code. |  |
| Educate and train stakeholders through outreach activities. Presentations Workshops Publications |  |
| Define regulatory review and business processes. |  |

## Major Project Deliverables

| Deliverable | Planned Completion Date |
| --- | --- |
| Compile a list of major safety questions along with critical information needed to address these questions | End of Q1, 2010 |
| Define the regulatory graphical review process/requirement to reinforce implementation of the safety graphics (to be further discussed). [For example, for PSAP efforts, recommendation/requirement for companies to submit PSAP at the end of phase II meetings] | End of Q1, 2010 |
| Create public repository of statistical graphics. Identify governance of the public repository for review, approval, and maintenance. | End of Q1, 2010 |
| Identify a location for collaborative development – this would be for internal working group members before being released to a larger audience. | April, 2010 |
| Develop the best practice and good principles for safety graphics | April, 2010 |
| Develop or identify several de-identified data sets for use in graphic development. | May, 2010 |
| Palette of statistical graphics for reporting clinical trials safety data. | May - Oct, 2010 |
| Identify classification system for graphics to be included in the site. Develop relevant documents, codes, and interpretation for each graphic. | Nov, 2010~ Jan, 2011 |
| Write best practices document/white paper/publication. | Nov, 2010 - March, 2011 |
| Training/Outreach: Conference presentations, workshops, and publications | 2nd Q, 2010 - 2nd Q, 2011 |

# Section 3 	Project Organization

## 3.1	Core Membership

  - Disciplines:  Statistics and clinicians.

    - FDA: Janelle Charles, Charles Cooper, Suzanne Demko, Richard Forshee, Eric Frimpong, Federico Goodsaid, Stephine Keeton, Leslie Kenna, Joyce Korvick, Antonio Paredes, George Rochester, Mat Soukup, Mark Walderhaug, Yaning Wang, Markus Yap

    - Industry : Richard Anziano, Fabrice Bancken, Navdeep Boparai,  Andreas Brückner, Brenda Crowe, Susan Duke, Sylvia Engelen, Robert “Mac” Gordon, Larry Gould, Liping Huang, Qi Jiang, Diane Kolb, Ken Koury, Catherine Njue

    - Academia: Mary Banach, Frank Harrell

- Key Stakeholders

  - Regulatory agencies.

  - Industry.

  - Academia institutions involved in conducting clinical trial research.

  - Patient groups and health care providers.

- Related Projects

  - OMOP

  - CSC (FDA)

  - CTAB

  - EMEA (EU)

  - SPERT

  - BDMTG

- Future Meetings

  - Meetings will be scheduled once per month and at other times as needed.

## 3.2	Roles and Responsibilities

| Role | Responsibility |
| --- | --- |
| Working Group | Identify areas particularly applicable and/or useful to regulatory review in which graphics can enhance understanding of safety information. Make recommendations about the development of a palette of statistical graphics for reporting of clinical trial data. Make recommendations regarding the creation of a publicly-available repository of sample graphics (ensuring appropriate credits are given for contributions), including data sets and code. Engage in outreach activities. Educate and train stakeholders. Ensure the integrity, quality, and appropriateness. |
| Chairs | The Chairs provide leadership and facilitate meetings. Oversee the activities of the working group. Assist in the development of the agenda. Ensures that the decisions, actions, recommendations and other information related to the working group are appropriately disseminated and documented. Serve as a liaison to external groups. |
| Committee Members | To provide scientific and technical expertise in the principles and good practices useful for the development of a palette of statistical graphics. To address the strengths and limitations of graphics and data sets, especially with regard to the interpretation of results. To contribute solutions to methodological issues associated with; outreach, acquisition of data sets, code palette development, and the identification of areas of interest to be pursued within the scope of the Charter. To engage in an open exchange and information sharing on new and emerging topics in graphical visualization of safety data. |
| Project Coordinator | Defines project goals and timelines. Organizes and facilities meetings on a regular basis. Prepares action items for the working group. Manages communication among the group and stakeholders. Helps the group meets it objectives and deliverables. |

## 3.3	Project Facilities and Resources

| Resource Requirement | Responsibility |
| --- | --- |
| Conference Rooms | FDA/Industry |
| TeleConference | Project Manager (Bruce Weaver) |
| Website | Vanderbilt University (Frank Harrell) |

# Section 4 	Points of Contact

| Primary Contact | Name/Title/ Organization | Phone | E-mail |
| --- | --- | --- | --- |
| Bruce Weaver | FDA | 301-796-3646 | Bruce.Weaver@fda.hhs.gov |
| Secondary Contact |  |  |  |
| George Rochester | FDA | 301-796-0986 | George.Rochester@fda.hhs.gov |
| Mat Soukup | FDA | 301-796-1005 | Mat.Soukup@fda.hhs.gov |
| Industry Contact |  |  |  |
| Ken Koury | Schering-Plough | 908-740-2561 | Ken.Koury@spcorp.com |

# Section 5	Glossary

BDMTG

BIO - A biotechnology organization, providing advocacy, business development and communications services

CTAB

EMEA – A decentralized body of the European Union, its responsibility is the protection and

promotion of public and animal health, through the evaluation and supervision of

medicines for human and veterinary use.

ENAR – Eastern North American of the International Biometric Society.

EU – European Union

ICH – International Conference of Harmonization

ISS – Integrated Summary of Safety

JSM – Joint Statistical Meetings

Industry – The Pharmaceutical Research and Manufacturers of America represents the country’s

pharmaceutical research and biotechnology companies.

SPERT – Safety Planning Evaluation and Reporting Team

WNAR – Western North American Region of the International Biometric Society

# Section 6 	Revision History

| Version | Date | Name | Description |
| --- | --- | --- | --- |
| 1.0 | Jan 20, 2010 | George Rochester | Initial Draft in current format. |
| 1.1 | Jan 30, 2010 | Qi Jiang | Section 2.4 Deliverables |
| 1.2 | Feb. 2, 2010 | Bruce Weaver | Project Plan, Responsibilities, and Points of contact updated. |
| 1.3 | June 2, 2010 | Bruce Weaver | Membership updated |